## Website timeline
Sr No. | Work | Assigned To | Priority | Start Date | End Date | Status | Remarks | 1 - Highest Priority
| Website template | Prince | 1 | 2016-08-25 | 2016-08-27 | Ongoing |  | 10 - Lowest Priority
| Logo | Prince | 2
| Data for website - matrix file | Prince
| Data for website - pictures | Prince | 2
| Email sending framework | Karan | 5
| 1st Email sending | Prince | 2
| Dynamic Jewelery lane minimum working | Karan | 2 | 2016-08-25 | 2016-08-25 | Done
Dynamic Jewelery lane
| Template Integration | Karan | 2
| Account creation - Admin (without email) |  | 2 | 2016-08-25 | 2016-08-26 | Ongoing
| Account creation - User (without email) |  | 2 | 2016-08-25 | 2016-08-26 | Ongoing
| Admin panel - Upload facility |  | 2
| Admin panel - Delete/update facility |  | 3
| Admin panel - Bulk upload | Prince | 4
| Favourite button on each item | Karan | 10
| User panel - display favourite button | Karan | 10
| User panel - Delete favourite facility |  | 3
| User panel - Update personal information - Name, Password |  | 3
| User creation - email authentication |  | 5
| Images auto web optimize | [5 empty] | Multiple Image Upload + Image Thumbnail Creation
Export to excel functionality

## Daily Progress
2016-08-25
Login page
Registration
Front lane dynamic

## Tasks
Sr No. | Work | Assigned To | Start Date | End Date | Status | Remarks
| BitBucket account | Karan
What to show on front page
Checkin sql dump

## Details to enter for diamonds
Mysql columns | Sample value
size | 1.0 ct.
shape | Round/Princess/Marquise/Emerald/Pear/Heart/Oval/Cushion/Radiant/Cus. Brilliant/Lradiant/SQEmerald
color | D/E/F/G/H/I/J/K/L/M/N/O/P-Z
fluorescence | None/FNT/MED/STG/VST
cut | EX/VG/G/F
clarity | FL/IF/VVS1/VVS2/VS1/VS2/SI1/SI2/SI3/I1
polish | EX/VG/G/F
lab | None/GIA/HRD/IGI
description