## Website timeline
Sr No. | Work | Assigned To | Priority | Start Date | End Date | Status | Remarks | 1 - Highest Priority
1 | Website template | Prince | 1 | 2016-08-25 | 2016-08-27 | Ongoing |  | 10 - Lowest Priority
2 | Logo | Prince | 2
3 | Data for website - matrix file | Prince
4 | Data for website - pictures | Prince | 2
5 | Email sending framework | Karan | 5
6 | 1st Email sending | Prince | 2
7 | Dynamic Jewelery lane minimum working | Karan | 2 | 2016-08-25 | 2016-08-25 | Done
8 | Dynamic Jewelery lane
9 | Template Integration | Karan | 2
10 | Account creation - Admin (without email) |  | 2 | 2016-08-25 | 2016-08-26 | Ongoing
11 | Account creation - User (without email) |  | 2 | 2016-08-25 | 2016-08-26 | Ongoing
12 | Admin panel - Upload facility |  | 2
13 | Admin panel - Delete/update facility |  | 3
14 | Admin panel - Bulk upload | Prince | 4
15 | Favourite button on each item | Karan | 10
16 | User panel - display favourite button | Karan | 10
17 | User panel - Delete favourite facility |  | 3
18 | User panel - Update personal information - Name, Password |  | 3
19 | User creation - email authentication |  | 5
20 | Images auto web optimize | [5 empty] | Multiple Image Upload + Image Thumbnail Creation
21 | Export to excel functionality
22 | Session management
23 | Multi-lingual option
24 | Browse button with default selection of images only
25 | Website information - contact us: email, address - about us | Prince
26 | Testsite authentication flag & box
27 | Install CentOS 6 + LAMP | Karan

## Daily Progress
2016-08-25
Login page
Registration
Front lane dynamic

## Tasks
Sr No. | Work | Assigned To | Start Date | End Date | Status | Remarks
| BitBucket account | Karan
What to show on front page
Checkin sql dump

## Details to enter for diamonds
Mysql columns | Sample value
size | 1.0 ct.
shape | Round/Princess/Marquise/Emerald/Pear/Heart/Oval/Cushion/Radiant/Cus. Brilliant/Lradiant/SQEmerald
color | D/E/F/G/H/I/J/K/L/M/N/O/P-Z
fluorescence | None/FNT/MED/STG/VST
cut | EX/VG/G/F
clarity | FL/IF/VVS1/VVS2/VS1/VS2/SI1/SI2/SI3/I1
polish | EX/VG/G/F
lab | None/GIA/HRD/IGI
description